Great! AI can see:

- ✅ Backend has axios NOT installed (Django doesn't need it)

- ✅ Frontend has axios ready

- ✅ Backend has CORS configured (but port 3000, needs update to 5173 for Vite)

- ✅ Backend has all needed packages (Django, DRF, Supabase, WeasyPrint, etc.)

Now here's your Step 5: Integration & Cleanup Roadmap:

📋 STEP 5: INTEGRATION & CLEANUP ROADMAP

🎯 Goals

- Wire frontend to backend APIs (replace all mock data)

- Align naming conventions between frontend/backend

- Implement real authentication with JWT

- Clean up hardcoded values, placeholders, and unused code

- Make both projects deployment-ready and maintainable

- Ensure frontend can work with any backend, backend can work with any frontend

✅ Your Observations Are Correct!

- Backend is ~90% done ✅ (just needs real auth + minor tweaks)

- Most work is frontend ✅ (wiring + cleanup + alignment)

- We clean as we integrate ✅ (not two separate phases)

🗓️ DAY-BY-DAY EXECUTION PLAN

DAY 1: Foundation Setup & Real Authentication

Goal: Set up communication infrastructure and implement proper auth flow

Step 1: Backend - CORS & Environment Setup

Sub-steps:

- Update settings.py CORS to allow Vite dev server (port 5173)

- Verify .env has all required keys (SECRET_KEY, SUPABASE_*, GOOGLE_MAPS_API_KEY, DB credentials)

- Test backend is running and accessible from frontend

Description: CORS blocks frontend calls if not configured. Vite runs on 5173, not 3000.

Step 2: Backend - Implement Real JWT Authentication

Sub-steps:

- Install djangorestframework-simplejwt

- Configure JWT in settings.py (token lifetime, auth classes)

- Replace hardcoded password check with proper check_password() in LoginAPIView

- Return JWT access/refresh tokens instead of dummy tokens

- Create a test police account with hashed password in DB (via Django shell or migration)

Description: Currently login uses testpass hardcode. We need real password hashing and JWT tokens.

Step 3: Frontend - Create API Service Layer

Sub-steps:

- Create src/services/api.js - Axios instance with base URL configuration

- Add interceptor to attach JWT token to all requests (from localStorage)

- Add interceptor to handle 401 (expired token) → redirect to login

- Create src/services/authService.js - login, logout, token refresh functions

Description: Centralize all API calls in one place. Makes switching backends easy.

Step 4: Frontend - Wire Real Login

Sub-steps:

- Update AuthContext.jsx login function to call backend /api/auth/login/

- Store JWT token (not dummy) in localStorage

- Parse and store user data from response

- Update logout to clear token and call backend if needed

- Add token expiry check on app load

Description: Replace mock login with real API call. Auth is now functional end-to-end.

Step 5: Testing & Verification

Sub-steps:

- Test login with correct credentials → dashboard loads

- Test login with wrong credentials → error message

- Test logout → redirects to login

- Test protected route access without login → redirects to login

- Check browser DevTools Network tab: JWT token in Authorization header

Description: Ensure auth works before moving to data wiring.

DAY 2: Dashboard & Reports Integration

Goal: Wire active reports list, detail view, and status updates

Step 1: Frontend - Create Reports Service

Sub-steps:

- Create src/services/reportsService.js

- Add functions: getActiveReports(), getReportDetail(id), updateReportStatus(id, status, remarks)

- Use the centralized API instance from Day 1

Description: Separate concerns - services handle API, components handle UI.

Step 2: Backend - Field Alignment Check

Sub-steps:

- Compare backend response fields vs frontend expectations

- Note differences (e.g., backend: reporter.first_name, frontend expects: reporterName)

- Document what needs to change (prefer changing frontend to match backend)

Description: Backend field names are already well-structured. Frontend should adapt.

Step 3: Frontend - Update Dashboard to Use Real Data

Sub-steps:

- Replace mock data in Dashboard.jsx with reportsService.getActiveReports()

- Add loading state during fetch

- Add error handling (show message if API fails)

- Map backend response fields to match component props:

  - reporter.first_name + reporter.last_name → reporterName

  - reporter.phone → reporterPhone

  - location_city → city

  - location_barangay → barangay

  - etc.

- Remove TemporaryDatabase.activeReports usage

Description: Components now display real database data. Mapping logic keeps components flexible.

Step 4: Frontend - Wire Report Detail Modal

Sub-steps:

- When "View" clicked, call getReportDetail(id) if not all data is in list response

- Update ReportDetailsModal to accept backend response format

- Handle missing fields gracefully (e.g., distance, eta initially null)

Description: Detail view may need full reporter info (emergency contact) not in list.

Step 5: Frontend - Wire Status Update

Sub-steps:

- When status dropdown changes in modal, call updateReportStatus(id, newStatus, remarks)

- Update local state after successful API call

- Show success/error notification (optional: toast library or simple alert)

- Refresh report list or update single item in state

Description: Police can now actually update report status in the database.

Step 6: Backend Cleanup - Remove Dummy Logic

Sub-steps:

- Verify all reports endpoints work with real data

- Add missing validation (e.g., status must be valid enum)

- Add comments to complex logic (nearest office assignment, geocoding)

Description: Polish backend while frontend is being wired.

DAY 3: Live Map & Checkpoints Integration

Goal: Display real map data and enable checkpoint management

Step 1: Frontend - Create Map & Checkpoint Services

Sub-steps:

- Create src/services/mapService.js - getMapData() calls /api/admin/map/data/

- Create src/services/checkpointsService.js - CRUD functions for checkpoints

Description: Map data comes from one endpoint; checkpoints have their own CRUD.

Step 2: Frontend - Wire Live Map Data

Sub-steps:

- In Map.jsx, replace mock data with getMapData()

- Parse response: active_reports, police_offices, active_checkpoints

- Map to marker format expected by Google Maps component

- Handle field alignment (backend uses assigned_office.office_name, etc.)

- Set up polling (every 30 seconds) to refresh map data

Description: Map now shows real-time data. Polling keeps it fresh.

Step 3: Backend - Verify Checkpoint Location Field

Sub-steps:

- Confirm Checkpoint model has location field (address string)

- Verify serializer returns it

- If missing, add field and update serializer

Description: Supabase schema added location column; ensure backend matches.

Step 4: Frontend - Wire Checkpoint CRUD

Sub-steps:

- AddCheckpointModal: on submit, call createCheckpoint() API

- EditCheckpointModal: on save, call updateCheckpoint(id) API

- Delete button: call deleteCheckpoint(id) API

- After each action, refresh checkpoints list or update state

- Handle assignedOfficers format: frontend uses array, backend accepts comma-separated string

Description: Officers can now manage checkpoints directly in the database.

Step 5: Frontend - Active/Inactive Logic Alignment

Sub-steps:

- Verify backend /api/checkpoints/active/ logic matches frontend filter

- If frontend calculates differently, use backend logic as source of truth

- Update UI filter to match backend behavior

Description: Consistency - don't calculate active status in two different ways.

DAY 4: Chat System & Directions Integration

Goal: Enable real-time messaging and navigation features

Step 1: Frontend - Create Messages Service

Sub-steps:

- Create src/services/messagesService.js

- Add getMessages(reportId), sendMessage(reportId, content, senderId, senderType, receiverId)

Description: Messages are nested under reports in the API.

Step 2: Frontend - Wire Chat Modal

Sub-steps:

- In ReportChatModal, replace mock data with getMessages(reportId)

- On send, call sendMessage() API

- Add polling (every 5 seconds) to fetch new messages

- Handle sender/receiver IDs correctly (police office ID vs user ID)

- Map backend timestamps to frontend display format

Description: Chat now works with real database. Polling simulates real-time.

Step 3: Backend - Add Google Maps API Key to .env

Sub-steps:

- Verify GOOGLE_MAPS_API_KEY is in backend .env

- Test /api/reports/{id}/route/ endpoint returns valid URL + QR

Description: Directions endpoint needs the key to generate QR/URL.

Step 4: Frontend - Wire Directions Modal

Sub-steps:

- When "Directions" clicked, call /api/reports/{id}/route/ API

- Use response directions_url and qr_code_base64

- Keep frontend haversine calculation as fallback if API fails

- Display both backend QR and frontend-calculated distance/ETA

Description: Backend provides official route; frontend can still show estimate.

Step 5: Frontend - Update Distance/ETA Display

Sub-steps:

- If backend response includes distance/duration from Google Directions API, use those

- Update state so ReportDetailsModal shows accurate info

- Add comment explaining fallback logic

Description: Accurate routing data improves police response.

DAY 5: Analytics & Resolved Cases Integration

Goal: Wire statistics, charts, and PDF exports

Step 1: Frontend - Create Analytics Service

Sub-steps:

- Create src/services/analyticsService.js

- Add functions: getOverview(filters), getLocationHotspots(filters), getCategoryStats(filters), exportAnalyticsPDF(filters)

Description: Analytics has multiple endpoints; centralize them.

Step 2: Frontend - Wire Analytics Page

Sub-steps:

- In Analytics.jsx, replace mock data with service calls

- Pass filter params (days, scope, office_id, city, barangay, category) to APIs

- Map response data to chart component format

- Handle empty results gracefully (show "No data" message)

- Wire "Export" button to trigger exportAnalyticsPDF() → download blob

Description: Charts now show real crime statistics.

Step 3: Frontend - Create Resolved Cases Service

Sub-steps:

- Create src/services/resolvedCasesService.js

- Add getResolvedCases(filters), exportResolvedCasesPDF(filters), exportSingleCasePDF(reportId)

Description: Resolved cases have their own filtering and export logic.

Step 4: Frontend - Wire Resolved Cases Page

Sub-steps:

- In ResolvedCases.jsx, replace mock data with getResolvedCases()

- Pass filter params to API

- Map response fields (resolution_time_str, etc.)

- Wire export buttons to download PDFs from backend

Description: Audit log now shows real closed cases.

Step 5: Backend - Test PDF Generation

Sub-steps:

- Manually trigger PDF export endpoints with test filters

- Verify WeasyPrint renders correctly (no missing Cairo errors)

- Check PDF content matches filters

- Add comments to PDF template logic if unclear

Description: Ensure PDFs work before frontend calls them.

DAY 6: Media Uploads & Final Cleanup

Goal: Implement file uploads and polish the entire app

Step 1: Frontend - Create Upload UI Component

Sub-steps:

- In ReportDetailsModal, add file input for attachments

- Create src/services/mediaService.js - uploadMedia(reportId, file, senderId)

- Handle file type validation (images/videos only)

- Show upload progress indicator

- Display uploaded files in modal

Description: Currently no upload UI exists. This completes the feature.

Step 2: Frontend - Wire Media Upload

Sub-steps:

- On file select, call uploadMedia() with FormData

- Backend returns file_url from Supabase

- Add URL to report's media list in state

- Display thumbnail or link to view file

Description: Evidence files now stored in cloud and linked to reports.

Step 3: Frontend - Remove All Mock Data

Sub-steps:

- Delete TemporaryDatabase.js

- Search codebase for "TemporaryDatabase" imports and remove

- Verify no hardcoded mock arrays remain

Description: Clean separation - no mock data mixed with real data.

Step 4: Frontend - Add Loading & Error States Everywhere

Sub-steps:

- Every API call should have: loading spinner, error message, success state

- Create reusable components: <Spinner />, <ErrorBanner />

- Consistent UX across all pages

Description: Professional app handles all states gracefully.

Step 5: Backend - Final Security & Config Review

Sub-steps:

- Set DEBUG = False in settings (for production checklist, not now)

- Verify SECRET_KEY is from environment, not hardcoded

- Add ALLOWED_HOSTS for production domain

- Review CORS: add production frontend URL

- Add rate limiting (optional - DRF throttle classes)

Description: Prepare backend for deployment.

Step 6: Frontend - Environment Variables Setup

Sub-steps:

- Create .env.example with template for required vars

- Document: VITE_API_BASE_URL, VITE_GOOGLE_MAPS_API_KEY

- Update API service to read from import.meta.env.VITE_API_BASE_URL

- Add .env to .gitignore (security)

Description: Easy to switch between dev/production backends.

Step 7: Code Cleanup & Comments

Sub-steps:

- Add JSDoc comments to all service functions (what they do, params, returns)

- Add inline comments to complex logic (status calculations, polling, etc.)

- Remove console.logs used for debugging

- Format code consistently (run Prettier/ESLint)

Description: Code should be readable by another developer (or you in 6 months).

DAY 7: Testing, Bug Fixing & Documentation

Goal: Ensure everything works end-to-end and document the system

Step 1: End-to-End Testing Scenarios

Sub-steps:

- Scenario 1: Login → View dashboard → Update report status → Logout

- Scenario 2: Login → Open map → Add checkpoint → Verify appears on map

- Scenario 3: Login → Open chat → Send message → Verify in DB

- Scenario 4: Login → Analytics → Apply filters → Export PDF → Verify download

- Scenario 5: Login → Resolved cases → View details → Export case PDF

Description: Test all major user flows work correctly.

Step 2: Edge Case Testing

Sub-steps:

- Test with no data (empty database) - does UI show "No results"?

- Test with invalid token (expired) - does app redirect to login?

- Test API failures (stop backend) - does UI show error message?

- Test long strings (names, descriptions) - does UI break?

- Test file upload with large file - does it handle gracefully?

Description: Robust apps handle edge cases without crashing.

Step 3: Bug Tracking & Fixes

Sub-steps:

- Create a simple bug list (text file or issue tracker)

- Prioritize: Critical (blocks features) → Minor (cosmetic)

- Fix critical bugs first

- Test fix → mark as resolved

Description: Systematic bug fixing prevents missing issues.

Step 4: Performance Optimization

Sub-steps:

- Check dashboard load time - should be < 2 seconds

- Optimize polling intervals (don't spam backend)

- Add pagination if report lists are huge (optional)

- Lazy load map markers if 100+ pins (optional)

Description: Fast app = better user experience.

Step 5: Documentation - Update README Files

Sub-steps:

- Backend README: Installation steps, env vars, run commands, API docs link

- Frontend README: Installation steps, env vars, run commands, project structure

- Overall README (root): Project overview, architecture diagram (simple text or image)

Description: Future you (or teammates) will thank you.

Step 6: Deployment Preparation Checklist

Sub-steps:

- Backend: Dockerfile ready, dependencies listed, env template

- Frontend: Build command works (npm run build), env vars documented

- Test production build locally before deploying

- Document deployment steps (Render/Fly backend, Netlify frontend)

Description: Deployment shouldn't be a mystery.

📊 SUCCESS CRITERIA (How to Know Each Day is Complete)

| Day | Must Pass Before Moving On |
| --- | --- |
| 1 | Login with real credentials works; JWT token visible in browser storage; protected routes redirect without token |
| 2 | Dashboard shows real reports from DB; status updates save to DB; no mock data used |
| 3 | Map shows real pins from DB; add/edit/delete checkpoint works; changes visible immediately |
| 4 | Chat loads real messages; send message appears in DB; directions show real route from backend |
| 5 | Analytics charts use real data; filters work; PDF exports download successfully |
| 6 | File upload works; all mock data deleted; loading/error states everywhere |
| 7 | All test scenarios pass; critical bugs fixed; README files complete |

✅ Project Success Criteria (How to Know Each Day is Complete)

This list outlines the minimum functionality that must be achieved each day before moving on to the next.

- Day 1: Login with real credentials works; JWT token visible in browser storage; protected routes redirect without token.

- Day 2: Dashboard shows real reports from DB; status updates save to DB; no mock data used.

- Day 3: Map shows real pins from DB; add/edit/delete checkpoint works; changes visible immediately.

- Day 4: Chat loads real messages; send message appears in DB; directions show real route from backend.

- Day 5: Analytics charts use real data; filters work; PDF exports download successfully.

- Day 6: File upload works; all mock data deleted; loading/error states everywhere.

- Day 7: All test scenarios pass; critical bugs fixed; README files complete.

🎓 LEARNING NOTES (For Your Growth)

Key Concepts You'll Master:

- Separation of Concerns: API logic (services) vs UI logic (components)

- Authentication Flow: JWT tokens, protected routes, token refresh

- State Management: When to use Context vs local state

- API Design: RESTful endpoints, proper HTTP methods, error responses

- Deployment: Environment variables, CORS, production vs development

Best Practices You'll Learn:

- Never hardcode secrets (API keys, passwords) - always use .env

- Always handle loading/error states - apps fail gracefully

- Comments explain WHY, not WHAT - code shows what, comments show reasoning

- Test before deploying - catch bugs locally, not in production

- Document as you build - easier than documenting later

✅ YOUR POINTS ADDRESSED

✅ Frontend/Backend Alignment: Days 2-6 explicitly map fields and align naming
✅ Independence: Service layer (Day 1) makes swapping backends easy
✅ Comments: Day 6 Step 7 adds comprehensive comments
✅ Backend 90% Done: Confirmed - mostly frontend work (you're right!)
✅ Cleanup While Integrating: Every day includes cleanup sub-steps
✅ Learning Mindset: Learning notes section + explanations in each step